APPENDIX C:	Campaign Timeline

Asheville Area Chamber of Commerce

Advantage Asheville

| Phase I August-September 2005 Identify and recruit campaign leadership Complete prospect identification, screening and rating Develop and produce campaign materials Solicit top tier prospects | Phase II October 2005-March 2006 Secure benchmark commitments Selected leadership functions Intense solicitation of all business sectors and selected individuals Kick-off in conjunction with new building ribbon cutting Complete all initial meetings and presentations Solicit entire existing investor base Solicit new investor prospects | Phase III April-May 2006 Follow up and closure Close out function? Records hand-off Initiate investor relations |
| --- | --- | --- |