Asheville Area Chamber of Commerce

Advantage Asheville 2010

60 Day Action Plan

August 25, 2005

Week of 8/22:		Final presentation of assessment findings

Board approval of campaign

First Kitchen Cabinet meeting

- Finalize Steering Committee prospect list

- Review and finalize naming opportunities

- Discuss other campaign related issues

Prepare Steering Committee recruitment letters

Follow-up meeting with Daniels Graphics in regard to the campaign brochure

Continue development of campaign master prospect list

Weeks of:		Steering Committee recruitment letters mailed and begin

August 29		recruitment/solicitation of Committee members

September 5

September 12		Continue development of campaign brochure

Screening and rating of master prospect list

Begin solicitation of first tier prospects

Weeks of:		Finalize Steering Committee recruitment

September 19

September 26		Review draft brochure

October 3

2nd Kitchen Cabinet meeting

Weeks of:		Finalize brochure

October 10

October 17		Begin general campaign solicitation