ECONOMIC DEVELOPMENT CORPORATION OF ELKHART COUNTY

ASSESSMENT CALENDAR

(September – October/November 2004)

Week 1					Develop assessment participation list

# Develop pre-approach letter

Develop Pre-Case Document

Rate & screen prospects

# Finalize assessment questionnaire

Week 2 					Mail out Pre-approach letters

# Schedule Assessment interviews

Conduct selected Board interviews

Weeks 3, 4, 5, 6				Conduct Assessment interviews

Conduct 1 – 2 Focus Group sessions

Week 6 & 7					Summarize findings and write report

Week 8 or 9	Present Assessment report to EDCEC Board of Directors